## Sheet1
Milestone: | M2 |  | estimated effort | remaining estimated effort | effort spent | 0100-Bader | 0700-Rigzin | 1300-Karthik
Week Ending: | 2018-02-28 |  | (person hours) | (person hours) | (person hours) | (person hours) | (person hours) | (person hours)
|  |  | 83 | 48 | 35 | 7 | 14 | 14
| Task Name | task description | original | remaining | total | effort spent by | effort spent by | effort spent by | estimated | Start-Date | Completion Date
Task # |  |  | estimated effort | estimated effort | effort spent | 0100-Bader | 0700-Rigzin | 0100-Karthik | percent | yyyy/mm/dd | yyyy/mm/dd
|  |  | (person hours) | (person hours) | (person hours) | (person hours) | (person hours) | (person hours) | complete | or N/A | or N/A
1 | FACT Table | List all the Facts and data types | 14 | 7 | 7 | 3 | 0 | 4 | 50% | 2018-02-21 | N/A
2 | Customer DIM Table | List all the DATTs and data types | 14 | 10 | 4 | 0 | 4 | 0 | 30% | 2018-02-21 | N/A
3 | Product DIM Table | List all the DATTs and data types | 15 | 11 | 4 | 4 | 0 | 0 | 26% | 2018-02-22 | N/A
4 | Dealer DIM Table | List all the DATTs and data types | 20 | 10 | 10 | 0 | 0 | 10 | 50% | 2018-02-21 | N/A
5 | Date DIM Table | List all the DATTs and data types | 10 | 0 | 10 | 0 | 10 | 0 | 100% | 2018-02-21 | N/A
6 | Role Playing DIM Table | List all the DATTs that are role playing | 5 | 5 | 0 | 0 | 0 | 0 | 0% | N/A | N/A
7 | Junk DIM table | LIst all the DATTs that doesn't fit in a particular DIM | 5 | 5 | 0 | 0 | 0 | 0 | 0% | N/A | N/A