## Sheet1
Milestone: | M2 |  | estimated effort | remaining estimated effort | effort spent | 0100-Bader | 0700-Rigzin | 1300-Karthik
Week Ending: | 2018-03-25 |  | (person hours) | (person hours) | (person hours) | (person hours) | (person hours) | (person hours)
|  |  | 114 | 0 | 37 | 6 | 12 | 19
Task # | Task Name | task description | original | remaining | total | effort spent by | effort spent by | effort spent by | estimated | Start-Date | Completion Date
|  |  | estimated effort | estimated effort | effort spent | 0100-Bader | 0700-Rigzin | 0100-Karthik | percent | yyyy/mm/dd | yyyy/mm/dd
|  |  | (person hours) | (person hours) | (person hours) | (person hours) | (person hours) | (person hours) | complete | or N/A | or N/A
1 | Customer IDD | List the all the level and the member in each level | 21 | 0 | 7 | 0 | 7 | 0 | 100% | 2018-03-08 | 2018-03-25
2 | Product IDD | List the all the level and the member in each level | 21 | 0 | 6 | 6 | 0 | 0 | 100% | 2018-03-08 | 2018-03-25
3 | Dealer IDD | List the all the level and the member in each level | 21 | 0 | 5 | 0 | 0 | 5 | 100% | 2018-03-08 | 2018-03-25
4 | Date IDD | List the all the level and the member in each level | 15 | 0 | 5 | 0 | 5 | 0 | 100% | 2018-03-08 | 2018-03-25
5 | Role Playing IDD | List the all the level and the member in each level | 12 | 0 | 3 | 0 | 0 | 3 | 100% | 2018-03-08 | 2018-03-25
6 | Junk DIM IDD | List the all the level and the member in each level | 12 | 0 | 3 | 0 | 0 | 3 | 100% | 2018-03-08 | 2018-03-25
7 | ERD | Conceptual Dimension model | 12 | 0 | 8 | 0 | 0 | 8 | 100% | 2018-03-08 | 2018-03-25